## Esitmations
Activity View | Description of the modification |  | Type | Needed information | Dev Wokloads | Test Workload | Tasks | Priority | Work Type
Configuration - Write to EPC | Write the EPC code into the tag. We get the EPC value from the asset instance. The objective is to check wether the Alien device can write EPCs with a length < 28. If that is the case, code should be updated in order to allow handling different epc sizes during the write operation |  | Adding / Updating |  | 3 | 2 | Check the documentation of the alien device |  | Standard | 0
[7 empty] | Check the configuration needed to accept diffrent sizes |  |  | 0
[7 empty] | integrate codes to allow the needed configuration in order to handle EPC with size < 28 |  |  | 0
Submit | Check the JSON format for audited and config and … |  | Updating ? | A clear explanation of the task | 0 | 0 |  |  | Standard | 0
Submit / Audit / Configuration | Check that the part number is serialized to server correctly |  | Updating |  | 2 | 0.5 |  |  | Standard | 0
Configuration - Write to EPC | Writing is difficult and it needs to be tested more to check what is the situation (it could be when we tagged a life vest there is some metal object that causes writing performance problems |  | Testing | Need the same life vest in order to reproduce the same experience | 0 | 0 |  |  | Standard | 0
Configuration | Add a datepicker to modify the value of the DoM |  | Adding | Visual preview of the expected result | 3 | 0.5 |  |  | Overtime | 3.5
Configuration | The objective is to eliminate already processed assets. Each time we execute correectly Writing / Reading /Action we remove the asset from the list of asset that remain to be proceeded |  | Updating |  | 3 | 1 | Add a new list of assets (that will represent the remaining assets to be processed) |  | Overtime | 4
[7 empty] | Add the removing process depending on a successfull execution of write and read |  | Overtime | 0
[7 empty] | maitain the remaining assets list |  | Overtime | 0
[7 empty] | add the mechanisim to retreive the final result (union of two lists processed and remaining) |  | Overtime | 0
Configuration | Modify the business case: when all the actions are performed for an asset it will automatically move to the next asset. No need to push a next button. |  | Updating | Do we remove the next button or not? If we do so will it be logicial to keep the previous button? | 3 | 1 |  |  | Overtime | 4
Configuration - Read barcode | when reading an incorrect barcode after reading a correct one the status should be set to reading status |  | Updating | Not clear need more clear explanation | 0 | 0 |  |  | Overtime | 0
Configuration | Each should be all shown when operating automatically |  | Updating ? | Not clear need more clear explanation (each what ?shown how?) | 0 | 0 |  |  | Overtime | 0
Configuration | Change the serial number and the codebar read as they are swapped (change the text box string) |  | Updating ? | Not clear need more clear explanation | 0 | 0 |  |  | Overtime | 0
Audit | considering the negative signed index the asset |  | Add |  | 3 | 1 |  |  | Overtime | 4
Check Barcode | The button check then load then check LOPA |  | Update? | Not clear need more clear explanations | 0 | 0 |  |  |  | 0
Summary
| Dev Workloads (H/M) | 17
| Test Workload (H/M) | 6
| Total overtime (H/M) | 15.5
| Total workloads (D/M) | 3.0667
| Availibility | 50
| Total workloads (H/M) | 23
| Work time (days) | 6.1333
| Total ($) - Hour Rate (25 usd) | 575
| Total overtime cost | 387.5

## MetaData
Type
Adding
Updating
Adding /Updating
Refactoring